## Report
Traceability Summary Report
Report Input
Requirements
List: PPR-1
Include child Issues: Yes (Child Issue Type filter: Bug, Story)
Cumulate requirements data: Yes
Include all Case Versions: No
Exclude Archived Cases: No
Cycles
Retrieve Runs: Yes, Retrieve Defects: Yes
List: PPR-CY-1
Statistic | Value | Explanation
Requirements | 13 | Requirement count.
Covered | 6 (46.2%) | Requirements having cases associated.
Not Covered | 7 (53.8%) | Requirements not having any cases associated.
Cases | 46 | Cases associated with covered requirements.
Defects | 7 | Defects uncovered while executing associated cases.
Requirement
Key | Summary | Type | Status | Priority | Coverage | Case Count | Execution Results | % Done | Defect Count
PPR-1 | User Functionality | Epic | To Do | Medium | Covered | 46 | 39 Passed, 7 Failed | 100.0% | 7
PPR-21 | Failed : While logged in, the user is able to create a planet with valid inputs. PNG Filetype should be supported. | Bug | To Do | High | Not Covered | 0
PPR-24 | Failed : While logged in, the user is able to create a moon with valid inputs. PNG Filetype Should be Supported | Bug | To Do | High | Not Covered | 0
PPR-25 | Failed : While logged in, the user is able to create a moon with valid inputs. PNG Filetype should be supported. | Bug | To Do | High | Not Covered | 0
PPR-19 | Failed : Users cannot register a new account with invalid credentials - Non-unique Username | Bug | To Do | Medium | Not Covered | 0
PPR-20 | Failed : While logged in, the user is not able to create a planet with invalid inputs. Expected Alert Not Present | Bug | To Do | Medium | Not Covered | 0
PPR-22 | Failed : While logged in, the user is not able to create a moon with invalid inputs. Expected Alert Not Present. | Bug | To Do | Medium | Not Covered | 0
PPR-23 | Failed : While logged in, the user is not able to create a moon with invalid inputs. Error Code Typo | Bug | To Do | Lowest | Not Covered | 0
PPR-2 | As a new user I want to open an account with the Planetarium so I can save my celestial findings. | Story | Done | Medium | Covered | 13 | 12 Passed, 1 Failed | 100.0% | 1
PPR-3 | As a user I want to securely access my account so I can interact with the Planetarium in a secure environment | Story | Done | Medium | Covered | 4 | 4 Passed | 100.0% | 0
PPR-4 | As a user I want to see my planets and moons added to the Planetarium so I can track my findings | Story | Done | Medium | Covered | 3 | 3 Passed | 100.0% | 0
PPR-5 | As a user I want to add new planets and moons to the Planetarium so I can update my findings | Story | Done | Medium | Covered | 18 | 12 Passed, 6 Failed | 100.0% | 6
PPR-6 | As a user I want to remove planets and moons from the Planetarium so I can correct my findings | Story | Done | Medium | Covered | 8 | 8 Passed | 100.0% | 0

## GraphData
Case Priority Distribution
Not Assigned | 46
Execution Distribution
Passed | 39
Failed | 7
Defect Distribution
To Do | 7